ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	3

2.2.	Specific objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	4

4.1.	General	4

4.2.	Specific work	4

4.3.	Project management	5

5.	LOGISTICS AND TIMING	5

5.1.	Location	5

5.2.	Start date & period of implementation of tasks	5

6.	REQUIREMENTS	5

6.1.	Personnel	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Serbia

## Contracting authority

Museum Ponišavlje Pirot, Nikole Pašića 49, 18300Pirot , Serbia

## Country background

Tourism is an area that is rapidly progressing. It is not only destinations that are in the focus of tourism, but also the culture and history of the people, the environment, biodiversity, developed infrastructure, and market-oriented services—in other words, all the components that contribute to a complete tourist offer. Therefore, modern tourism should be viewed as a whole, through a set of integrated segments that are interconnected and built upon one another.

Due to numerous market challenges and growing competition, tourism should not be territorially limited to a single city, region, or country. Instead, these limitations should be overcome. An innovative approach is needed—one that goes beyond physical and administrative borders and creates an integrated tourist area that extends across two or more countries. This increases competitiveness and creates a more original and recognizable tourist offer, one that can be easily identified on the geographical tourist map.

Countries oriented toward tourism should not perceive it solely from the standpoint of service providers, but rather from the perspective of the visitor and his needs. When passenger transit is significantly simplified, visitors can easily envision exploring all places of interest within one territorial zone, regardless of administrative boundaries. Visitors are guided by their interest in a certain location or culture, without considering which city or country it belongs to. For this reason, tourism must be approached in a more complex and holistic manner.

Border regions such as Pirot and Montana have both the privilege and the challenge of creating an integrated territory as a tourist package that meets visitors’ expectations and responds to their needs. In this sense, tourism in the border territory cannot be viewed solely within a local or national framework, but in a much broader context. The recognition of the region and its competitiveness—the main goals of this project—can be achieved only by looking beyond administrative borders and focusing on the structure, content, and originality of the tourist offer of the territory as a whole.

Project partners on both sides of the border benefit from adopting a cross-border approach to project implementation because their individual goals and visions become aligned with the overall integrated objective of the project. Additionally, through implementation, their capacities will be strengthened in terms of new working methods, communication models, and staff skills.

The multi-sector approach included in the project concept brings numerous benefits to various actors and target groups. These include:

- local self-governments in the Pirot–Montana region, which will experience long-term positive effects on economic growth and quality of life;

- tourism, economic, and other structural bodies, which will achieve better business results thanks to enhanced cooperation and jointly developed tourism promotion initiatives;

- NGOs, which will raise territorial recognition through cross-border activism and projects, increase public awareness of new tourism models, and at the same time improve their own skills and knowledge.

The project area—considering its tourist potential and the need to connect cultural heritage with tourist sites—cannot fully develop without a cross-border concept, especially with the introduction of innovative approaches in tourism throughout the target territory. Finally, thanks to the cross-border approach in project implementation, Specific Objective 2 of the Programme’s Territorial Strategy will be achieved.

## Current situation in the sector

This project introduces a broader concept for tourism development and the promotion of cultural and historical heritage by integrating regions in the pursuit of common goals and improved regional competitiveness. At the national level in both countries, the areas of culture and tourism are regulated by laws, strategies, and other legal acts that do not include a cross-border concept. As a result, these documents do not provide a wider framework for defining the development goals of local communities, which significantly reduces the competitiveness of the region. Museum Ponisavlje in Pirot belongs to the category of official museum institutions that studies, protects and presents cultural, artistic and historical works, i.e. movable museum assets. Its employees are experts in the field of culture, especially ethnology, with experience in the realization of cultural projects Museum exhibits displayed in display cases reflect the story of the development of human society since the beginning of the application of agriculture and the domestication of domestic animals.  The backbone of the Museum's educational content is made up of two permanent museum exhibits (the Old House of Pirot of the 19th century and the Permanent Archaeological Exhibit), occasional thematic exhibitions and events. The permanent motive of these activities is contained in the idea to provide the visitor with the most interesting content, as well as to involve the widest possible population in the activities. Events such as: Days of European Heritage, Museum Night or Museums of Serbia for 10 days from 10 to 10, with their thematic orientation, make the educational content of the museum more complete. These programs include interactive workshops, lectures, didactic exhibitions, etc. which complement and enrich the educational content of the Ponisavlja Museum.. During project implementation, in addition to reconstruction works on the fortresses, there will be organized  also several events in both sides of the border. Due to organized educative events, it will be  set new standards in work and better outputs. Also, NGOs as project actors, will intend  to raise the level of recognition of the territory, increasing people's awareness of new models of tourism, while at the same time improving their skills and knowledge through cross-border cooperation. Finally, through the promotion of the final results, local community will be encouraged to adopt the results of the project and to work further on their sustainability The target group and beneficiaries of the project are local and regional population (urban and rural), people and organisations actived in culture and toursim without any kind of discrimination (in terms of nationality, gender, social status, etc). Main relevant document on national level: Tourism Development Strategy of the Republic of Serbia 2016-2025. This project is aligned with the Strategy in terms of the segments related to tourism development goals, planning to increase competitiveness, planning in tourism, support and investment measures, etc.

- .

## Related programmes and other donor activities

Museum Ponisavlje has been umplemented several project financed financed by Mnistry of tourism  and one project -Carpet tale under CBC Programme Bulgaria -Serbia.

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) to which this action contributes is :

Overall objective is improved of capacity of local and regional stakeholders and target group, strengthening of educative recourse and promotion potential of Pirot-Montana CBC region.

The multi-sector approach applied in the project has many effects for various actors/target groups such  as :local self-governments as a public bodies in the territory of the Pirot-Montana region ,tourism and cultural organizations, entrepreneurs, youth.

Due to organized educative events, it will be  set new standards in work and better outputs. Also, NGOs as project actors, will intend  to raise the level of recognition of the territory, increasing people's awareness of new models of tourism, while at the same time improving their skills and knowledge through cross-border cooperation. Finally, through the promotion of the final results, local community will be encouraged to adopt the results of the project and to work further on their sustainability.

## Specific objective(s)

The  specific objective (Outcome)of this contract is as follows:

Contractor/service provider  should  support Museum Ponišavlje Pirot in events organization including  accomodation,  catering  and transport service of event participants.

## Expected outputs to be achieved by the contractor

The service will be paid on the basis of the delivery of the specified output(s). Payments might be totally or partially withheld if the contractual result(s) have not been reached in conformity with the detailed terms of reference. Payment(s) is/are based on the approval of this/these deliverable(s). Partial payment has to be determined according to the partial implementation of the output(s).

The expected outputs of this contract are as follows:

Output 1 to Outcome 1 : .Organized of   Tourist Forum in Serbia

Output 2 to Outcome 1  : Organized event:    Presentation of the improved cultural heritage - the fortress of Pirot /

Output 3 to Outcome 1  : Provided  transport for participants of forum in Bulgaria and local transport in Serbia

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

N/A

## Risks

N/a

# SCOPE OF THE WORK

## General

### Description of the assignment

The purpose of this contract is to support the Museum Ponišavlje Pirot in organization of events in Serbia and provision of local and international transport for event in Bulgaria.

It is a part of the project “Culturolling  stones ” funded under the INTERREG VI-A IPA Bulgaria–Serbia Programme.

The assignment includes the following  segments:

- Organization   Tourist Forum in Serbia ( Pirot, Pirot district)

A Regional Forum will be organized in Pirot or Pirot district , bringing together stakeholders to implement joint activities, exchange good practices, and acquire new knowledge aimed at creating opportunities for cross-border cooperation (CBC) in the preservation and promotion of cultural heritage in the Montana–Pirot region. The four-day Tourist Forum in Serbia will further focus on enhancing tourism potential, with cultural heritage recognized as a key asset, in line with the principles of the New European Bauhaus. Participants will strengthen their professional capacities and transfer acquired knowledge to increase the tourist attractiveness and support the sustainable economic development of the CBC region.

The Forum will involve 82 participants, including 40 representatives of institutions, organizations, local authorities, and cultural heritage professionals from the Montana District, 40 participants from the Pirot region, one interpreter, and one lecturer.

Provisional time of event Jun-septemebar 2026

- .Organization of final  event/ Presentation of the improved cultural heritage - the fortress of Pirot

Presentation of the improved cultural heritage - the fortress of Pirot  will be organized as a performance  of the Serbian/local  cultural heritage. It will take place also in  Pirot with participation of official 10 representatives of   Montana municipality , 10 From Pirot and all interested, and the community of the CBC region.  Event will be organized in Pirot for the presentation of reconstruction works with a cultural performance of local folklore with a demonstration of digitized products/applications as a result of the project.

Provisional time of event March-April 2027

- Transport service for travel of participants of Tourist forum  (42 people) in Bulgaria and local transport for Tourist forum participants in Serbia (40)

The contractor will be responsible for the end-to-end delivery of the contracted service.

Contracting authority(Museum Ponisavlje) will provide all the necessary informational support related to the project Culturaling stones which serves as the basis for the service implementation.

### Geographical area to be covered

Pirot, Pirot distrit  (Serbia), Montana district (Bulgaria) , cross border region

### Target groups

Project stakeholders in CBC region Bulgaria-Serbia  direct affected by project activities

## Specific work

The contractor has to provide complete service as following:

Implementation period : 14 months

1.Organized  Tourist Forum in SERBIA (Pirot, Pirot district)  - Provisional date : June -September  2026

1.1 Accommodation of participants  in Serbia  -hotel in Pirot or up to 30 km away from Pirot  82 participants  /40 representatives of institutions and organizations, local authorities and people working in the area of  culture preserving  from BG and 40 from SRB, 1 interpreter and 1 lecturer/  - 3 nights in single /double rooms

1.2	 Catering service - 82 participants/40 representatives of institutions and organizations, local authorities and people working in the area of  culture preserving  from BG and 40 from SER, 1 interpreter and 1 lecturer/ - 3 days - lunch and dinner

1.3	  Lunch   for 82 participants/40 representatives of institutions and organizations, local authorities and people working in the area of  culture preserving   from BG and 40 from SER, 1 interpreter and 1 lecturer/ - 1 day –

1.4. Coffee breaks for 4 days - 6 coffee breaks   x 82 participants

1.5 Provide/ rent of hall for 3 days Tourist forum event (82 participants)

2.	Organization of final event - Presentation of the improved cultural heritage - the fortress of Pirot /March-April 2027

2.1	 Catering service/ Lunch  and dinner for 1 day for 10 participants /representatives of Pirot

2.2	  Catering service  /lunch and dinner for 2 days for 11 participants /10 representatives of Montana  municipality and 1 interpreter/ - and 2 days *4 coffe break*22participants

2.3	 Accommodation  in a single/double  room in hotel in Pirot or up to 30 km away from Pirot  for 11 participants /10 representatives of Montana  municipality and 1 interpreter/ - 11 participants x 1  night

2.4 Organization of the event - materials and sound

- sounds  for technical support of the event ( location Kale Fortress or hall  )

- Material for participants : set  folder and pencil , notebook  B5 for 21 participants

MENY STRUCTURE FOR ALL EVENTS:

- BUFFET MENU – LUNCH

Starters & Salads (approx. 250 g per person)

- Seasonal mixed salad

- Cabbage or carrot salad

- Cheese and light cold cuts

Main Course (300 g)

- Meat option: chicken / pork / beef/fish

- Vegetarian option: vegetable risotto or pasta

Side Dishes (150 g)

- Potatoes and seasonal vegetables or rice

Bread & Pastries (100 g)

Dessert (120 g)

- Fruit or cake

Non-alcoholic beverages 200ml

Juice /water

- BUFFET MENU – DINNER 82 participants

Starters & Salads (approx. 250 g per person)

- Seasonal mixed salad

- Pasta or potato salad

- Cheese

Main Course (250 g)

- Meat option: roasted meat or fish

- Vegetarian option: roasted or grilled vegetables with side dish

Side Dishes (120 g)

- Rice, potatoes, or vegetables

Bread & Pastries (100 g)

Light Dessert or Fruit (100 g)

Non-alcoholic beverages 200 ml

Juice /water

- COFFEE BREAK

Beverages (per person)

- Coffee – 200 ml/ Tea – 200 ml

- Water (still and sparkling) – 200 ml

Snacks / Light Bites (per person, approx. 150–200 g total)

- Assorted pastries / biscuits – 80 g

3. Transportation costs

3.1 International Travel Costs

International travel costs include organized passenger transport for 42 participants from Pirot (Republic of Serbia) to Varshets (Republic of Bulgaria), covering outbound travel to the Forum venue and return travel after 4 days, by bus or other appropriate means of transport.
The contractor shall bear all costs related to obtaining the necessary documentation and permits for international passenger transport, in accordance with applicable national and international regulations.

Provisional  time of travel:  april  2026

3.2 Local and Regional Travel Costs

Local and regional travel costs include passenger transport for 40 Forum participants within the territory of the Republic of Serbia, related to participation in Forum activities, including transport to and from the Forum venue and associated locations.
The costs are based on an estimated total distance of 300 km using bus or other appropriate means of transport, in compliance with applicable safety and technical standards.

The service includes the organization of transportation for participants to the forum from the Pirot District to the place of event organisation, including participants form Pirot district, according to the provided schedule for the planned 40 participants.

The contractor shall be informed of the exact dates of the services at least 10 days in advance.

The contractor must also comply with the latest Communication and Visibility Requirements for EU-funded external action, laid down and published by the European Commission. The compliance with this shall be made an output of the contract and the contractors shall include in its reporting what have been accomplished.

## Project management

### Responsible body

Museum Ponišavlje Pirot -Contracting authority

### Management structure

The responsible person for implementation of the tasks related to this contract, in the Contracting Authority is Bojan Randjelović, legal representative and coordinator for project activities in  behalf of organisation.

### Facilities to be provided by the contracting authority and/or other parties

The Contracting Authority will provide all necessary data and information related to implementation of this Contract

# LOGISTICS AND TIMING

## Location

The project activities related to this Contract will be realized in the territory covered by  City of  Pirot /Pirot district Serbia   and Municipality Montana ( district) Bulgaria

## Start date & period of implementation of tasks

The intended start date is date of contract signature and the period of implementation of the contract will be < 14> months from this date. Please see point 3 of the main conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Personnel

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be able to provide input as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well on any potential interference or conflict of interest of the proposed expert in his/her function as expert and his/her present or previous functions working as civil servant. Moreover proof should be submitted that the expert is seconded or on personal leave.

The selection procedures used by the contractor to select the experts who provide input to the contract must be transparent, must guarantee the absence of professional conflicting interests and the absence of any discrimination based on former or current nationality, gender, place of residence, or any other ground. The findings of the selection panel must be recorded.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Experts

Minimum requirements for experts are not defined.

### Support facilities & backstopping

The costs for support facilities, including backstopping, are included in the tenderer's financial offer.

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The contractor shall select and hire other experts as required according to the needs. The selection procedures used by the contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

## Office accommodation

Office accommodation for each expert providing input to the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English  in one original and 1 copies:

- Inception Report of maximum 12 pages to be produced after 1 month from the start of implementation. In the report the contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The contractor should proceed with his/her work unless the contracting authority sends comments on the inception report.

- Interim Report The contractor will prepare interim reports on the implementation of the tasks, at the 6 th month and  of contract service implementation. The report shall contain a detailed description of the implemented services for the reported period.  The interim reports must be provided along with the corresponding invoice. The interim report should be approved by the Contracting authority.

Draft final report of maximum 20 pages (main text, excluding annexes. This report shall be submitted no later than one month before the end of the period of implementation of tasks.

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 15 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on delivered service.. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is -Service provided on time, quality, in full and in accordance with Terms of Reference”

## Special requirements

N/A

* * *